## Testing record
Component | Objective | Test | Expected | Actual | PassFail | Issue | Action | Retest | CollaboratingTrack | Evidence
Week 6 candidate (GB) | Reproducibility | T1 re-run Week 6 CV protocol | AUC 0.505; confusion [[221,4235],[21,523]] | AUC 0.5049; confusion reproduced exactly | PASS | None | None | n/a | Data Science | Notebook s.2 T1
Week 6 candidate (GB) | Performance on unseen data | T2 locked 20% hold-out | AUC >= 0.60, CI above 0.5 | AUC 0.479 (95% CI 0.423-0.535) | FAIL | No discrimination on unseen data | Refined (R1-R3) | AUC 0.455 (95% CI 0.398-0.513) -> FAIL | Data Science | Fig w7_fig01
Week 6 candidate (GB) | Stability | T3 10 repeated grouped CV | 90% of runs AUC>0.55 | 0% of runs AUC>0.55; mean 0.504 | FAIL | Unstable and near chance | Refined | 0% of runs AUC>0.55; mean 0.480 -> FAIL | Data Science | Notebook T3
Week 6 candidate (GB) | Signal vs chance | T4 label permutation (100) | p < 0.05 | p = 0.416 | FAIL | Observed AUC inside null distribution | Refined | p = 0.733 -> FAIL | Data Science | Fig w7_fig01
Week 6 candidate (GB) | Over-fitting | T5 train vs validation AUC | Gap <= 0.05 | train 0.746 - validation 0.506 = 0.240 | FAIL | Severe over-fitting (I1) | R2 regularised model | train 0.549 - validation 0.486 = 0.063 -> FAIL | Data Science | Fig w7_fig05
Week 6 candidate (GB) | Time validity | T6 train Jan-Aug, test Sep-Dec | AUC >= 0.55 | AUC 0.467 (CI 0.427-0.513) | FAIL | Below chance in the future period | Refined | AUC 0.484 (CI 0.440-0.532) -> FAIL | Data Science | Notebook T6
Week 6 candidate (GB) | Calibration | T7 slope and Brier | Slope 0.8-1.2 | slope 0.10 (CI -0.25-0.45); Brier 0.0975 vs prevalence 0.0970 | FAIL | Probabilities carry no information | Refined | slope -0.27 (CI -0.84-0.30); Brier 0.0973 vs prevalence 0.0970 -> FAIL | Data Science | Fig w7_fig02
Week 6 candidate (GB) | Operating point | T8 policy comparison | Sensible flag rate, lift > 1.3 | F1 threshold flags 95%, lift 1.01x; top-20% lift 1.06x | FAIL | Degenerate threshold (I3) | R3 flag-rate budget | top-20% lift 0.85x (hold-out) - policy now interpretable; still no value | Data Science | Fig w7_fig02
Week 6 candidate (GB) | Error patterns | T9 FP vs TN, FN vs TP at top-20% | Identifiable, fixable error groups | flagging driven by FacilityID, BMI_clean, Age (Holm p<0.001) but positive rate flagged 0.115 vs unflagged 0.107 | FAIL | Score follows noise (facility, BMI, age): flagged = unflagged in outcome | R1 removed facility/BMI/department | Refined model has no facility/BMI input; still no outcome signal | Data Science | Notebook T9
Week 6 candidate (GB) | Segment parity | T10 sex/age/province/facility | Gap <= 10 pp | max recall gap 20.5 pp; max flag-rate gap 22.5 pp | FAIL | None systematic; AUC ~0.5 everywhere | None | max recall gap 29.3 pp; max flag-rate gap 35.6 pp -> FAIL | Data Science | Fig w7_fig03
Week 6 candidate (GB) | Feature validity | T11 audit, ablation, leakage | All features reliable and informative | 4 unreliable; ablation deltas within noise; no leakage found; importance>2SD: 0/14 | FAIL (I2) | Unreliable features in model | R1 removed 4 features | Ablation: no AUC loss; model simpler | Data Analytics | Notebook T11
Test harness | Can the harness detect signal? | T12 positive controls + target scan | Controls recovered; other targets reveal any signal | Controls recovered: True; detected non-control outcomes: ['Returning patient (PriorVisits>0)'] (returning-patient: month artifact, vanishes when month removed) | PASS | No signal in the data (I6) | Escalated to PM / data owner | n/a | Project Management | Fig w7_fig04
Week 6 candidate (GB) | Meaningful improvement over baseline | Paired bootstrap delta-AUC | delta >= 0.05, CI > 0 | delta-AUC 0.006 (95% CI -0.028 to 0.039) | FAIL | No improvement over prevalence baseline | Refined | delta-AUC -0.015 (95% CI -0.049 to 0.018) -> FAIL | Data Science | Notebook s.4
Model interface | Safe hand-off to ML pipeline | C1-C15 contract tests | 15/15 pass | 10/15 pass | FAIL | Silent failures (I5) | Validated scorer wrapper + schema | 15/15 pass; fresh-process exit code 0 | None available: Data Science side only | outputs_w7/handoff_ml_engineering; contract_tests_*.csv
Analytical findings | Are the findings that drive modelling decisions correct? | Independent recomputation from raw files | Week 6 values reproduced | 5 of 5 confirmed; 1 new finding | PASS | New: Follow-Up visits without history | Reported to Data Analytics / PM | Decisions D3 confirmed | Data Analytics (Olabisi Amusan): validated both ways | Notebook s.7
Release gate | Is the model suitable? | Gate on AC1-AC10 | All mandatory criteria pass | As built: FAIL; refined: FAIL | FAIL | Mandatory criteria not met | Not released for operational use (D5) | Re-run when outcome data exist | Project Management | Gate tables s.4-5

## Acceptance criteria
ID | Type | Criterion | Pass rule
AC1 | S | Reproducibility | Re-running the Week 6 protocol reproduces the reported AUC (0.505) within +/-0.005
AC2 | M | Discrimination on locked test set | Hold-out AUC >= 0.60 and the lower 95% bootstrap bound > 0.50
AC3 | M | Operational value | Precision in the top-20% highest-scored appointments (lift) >= 1.30 x prevalence, lower bound of lift > 1.0
AC4 | S | Stability | At least 90% of 10 repeated grouped-CV runs have AUC > 0.55
AC5 | M | Signal vs chance | Label-permutation test p < 0.05
AC6 | S | Calibration | Calibration slope within 0.8-1.2 and Brier score better than the prevalence-only forecast
AC7 | S | Over-fitting | Train-minus-validation AUC gap <= 0.05
AC8 | S | Time-based validity | AUC >= 0.55 when trained on Jan-Aug and tested on Sep-Dec
AC9 | M | Meaningful improvement over baseline | Paired-bootstrap delta-AUC vs baseline >= 0.05 with the 95% lower bound > 0
AC10 | S | Segment parity | Recall and flag-rate gap between sex, age-band and province groups <= 10 percentage points (groups with n >= 100)

## Gate - Week 6 candidate
ID | Type | Criterion | Observed | Result
AC1 | S | Reproducibility | max ¦diff¦ = 0.0008 | PASS
AC2 | M | Hold-out discrimination | AUC 0.479 (95% CI 0.423-0.535) | FAIL
AC3 | M | Operational lift (top 20%) | lift 0.78x (95% CI 0.44-1.15) | FAIL
AC4 | S | Stability (10 runs) | 0% of runs AUC>0.55; mean 0.504 | FAIL
AC5 | M | Permutation test | p = 0.416 | FAIL
AC6 | S | Calibration | slope 0.10 (CI -0.25-0.45); Brier 0.0975 vs prevalence 0.0970 | FAIL
AC7 | S | Over-fitting gap | train 0.746 - validation 0.506 = 0.240 | FAIL
AC8 | S | Time-based AUC | AUC 0.467 (CI 0.427-0.513) | FAIL
AC9 | M | Improvement vs baseline | delta-AUC 0.006 (95% CI -0.028 to 0.039) | FAIL
AC10 | S | Segment parity | max recall gap 20.5 pp; max flag-rate gap 22.5 pp | FAIL

## Gate - refined
ID | Type | Criterion | Observed | Result
AC1 | S | Reproducibility | n/a (new model) | n/a
AC2 | M | Hold-out discrimination | AUC 0.455 (95% CI 0.398-0.513) | FAIL
AC3 | M | Operational lift (top 20%) | lift 0.85x (95% CI 0.54-1.18) | FAIL
AC4 | S | Stability (10 runs) | 0% of runs AUC>0.55; mean 0.480 | FAIL
AC5 | M | Permutation test | p = 0.733 | FAIL
AC6 | S | Calibration | slope -0.27 (CI -0.84-0.30); Brier 0.0973 vs prevalence 0.0970 | FAIL
AC7 | S | Over-fitting gap | train 0.549 - validation 0.486 = 0.063 | FAIL
AC8 | S | Time-based AUC | AUC 0.484 (CI 0.440-0.532) | FAIL
AC9 | M | Improvement vs baseline | delta-AUC -0.015 (95% CI -0.049 to 0.018) | FAIL
AC10 | S | Segment parity | max recall gap 29.3 pp; max flag-rate gap 35.6 pp | FAIL

## Contract tests before
ID | Scenario | Expected | Result | Detail
C1 | Valid batch of 5 | Scores in [0,1], no null | PASS | 5 rows, scores 0.092-0.108
C2 | Single row | Scored | PASS | 1 row
C3 | Missing numeric values | Scored (imputed) | PASS | numeric null handled
C4 | Missing categorical value | Scored, flagged | PASS | categorical null handled
C5 | Unseen category ('Zanzibar' in a categorical column) | Scored AND visible in status | FAIL | row status: SCORED
C6 | Required column missing | Clear error naming the column | PASS | ValueError: columns are missing: {'Age'}
C7 | Extra unexpected column | Ignored, scores unchanged | PASS | extra column ignored, scores unchanged
C8 | Columns in different order | Same scores | PASS | column order does not matter
C9 | Numbers sent as text ('45') | Coerced, same scores | PASS | numeric strings coerced
C10 | Non-numeric value ('abc') in Age | Bad row rejected, rest of batch scored | FAIL | EXCEPTION ValueError: Cannot use median strategy with non-numeric data: could not convert string to float: 'abc'
C11 | Impossible values (Age 250, PriorVisits -3) | Bad rows rejected, rest scored | FAIL | Age=250 and PriorVisits=-3 rejected, rest scored
C12 | Wrong text case ('female','MALARIA') | Normalised, same scores | FAIL | case differences normalised
C13 | Empty input | Empty output, no crash | FAIL | EXCEPTION ValueError: Found array with 0 sample(s) (shape=(0, 8)) while a minimum of 1 is required by SimpleImputer.
C14 | Repeat call determinism | Identical output | PASS | identical output on repeat call
C15 | Duplicate row index | Scored | PASS | duplicate index handled

## Contract tests after
ID | Scenario | Expected | Result | Detail
C1 | Valid batch of 5 | Scores in [0,1], no null | PASS | 5 rows, scores 0.097-0.125
C2 | Single row | Scored | PASS | 1 row
C3 | Missing numeric values | Scored (imputed) | PASS | numeric null handled
C4 | Missing categorical value | Scored, flagged | PASS | categorical null handled
C5 | Unseen category ('Zanzibar' in a categorical column) | Scored AND visible in status | PASS | row status: SCORED_WITH_WARNINGS: Diagnosis unseen category 'Zanzibar'
C6 | Required column missing | Clear error naming the column | PASS | SchemaError: Missing required column(s): ['Age']. Expected: ['Age', 'PriorVisits', 'MonthNum', 'WeekdayNum', 'DoctorYears',
C7 | Extra unexpected column | Ignored, scores unchanged | PASS | extra column ignored, scores unchanged
C8 | Columns in different order | Same scores | PASS | column order does not matter
C9 | Numbers sent as text ('45') | Coerced, same scores | PASS | numeric strings coerced
C10 | Non-numeric value ('abc') in Age | Bad row rejected, rest of batch scored | PASS | row 1 rejected, rows 2-5 scored
C11 | Impossible values (Age 250, PriorVisits -3) | Bad rows rejected, rest scored | PASS | Age=250 and PriorVisits=-3 rejected, rest scored
C12 | Wrong text case ('female','MALARIA') | Normalised, same scores | PASS | case differences normalised
C13 | Empty input | Empty output, no crash | PASS | empty input returns empty output
C14 | Repeat call determinism | Identical output | PASS | identical output on repeat call
C15 | Duplicate row index | Scored | PASS | duplicate index handled

## Analytics validation
Analytical finding (Week 6) | Week 6 value | Independent re-computation (raw files) | Confirmed | Effect on modelling decision
Appointment facility differs from department's owning facility | 94.9% (4,744 rows) | 94.9% (4,744 rows) | CONFIRMED | FacilityID and DepartmentName removed (R1); ablation shows no AUC loss
Bills whose appointment is missing | 55,000 | 55,000 | CONFIRMED | Appointment-level modelling limited to 5,000 linked rows
Diagnoses whose appointment is missing | 55,000 | 55,000 | CONFIRMED | Same limit; more modelling data cannot be obtained until keys are repaired
Appointments dated after 24 Oct 2026 | 874 | 874 | CONFIRMED | Sensitivity test T11d: excluding them does not change AUC
Bill Status label carries no payment information | Paid 90.0% / Partial 90.1% / Pending 90.2% paid (p=0.643) | Paid 90.0% / Partial 90.1% / Pending 90.2% paid (p=0.643) | CONFIRMED | BillStatus never used as a feature (satisfaction model excluded it from conclusions)
Follow-Up visits with no earlier visit in the extract (NEW) | not reported in Week 6 | 88.0% | NEW | NEW finding for Data Analytics: VisitType or the extract's history is incomplete; PriorVisits is a truncated-history feature

## Issue log
ID | Issue | Severity | Owner track | Status | Action / resolution
I1 | Over-fitting in the Week 6 candidate (train AUC 0.75 vs validation 0.51) | High | Data Science | MITIGATED | Regularised model on reliable features (R1, R2): gap 0.06 (AC7 limit 0.05 still narrowly missed)
I2 | Unreliable features (facility/department 94.9% mismatch, BMI for minors) inside the model | High | Data Science / Data Analytics | RESOLVED | Removed; ablation shows no performance loss (T11b)
I3 | F1-maximising threshold flags 95% of appointments (lift 1.0x) | Medium | Data Science | RESOLVED | Top-20% flag-rate budget with lift reporting (R3)
I4 | No release gate: a no-signal model could be deployed | High | Data Science / Project Management | RESOLVED | Executable gate AC1-AC10 (R4); result recorded in schema.json
I5 | Silent failures at the model interface (impossible values, mis-cased text, whole-batch failures) | High | Data Science / ML Engineering | RESOLVED (DS side); no ML Engineering counterpart available | Scorer wrapper; contract tests 10/15 -> 15/15
I6 | No predictive signal in any available feature or alternative target (data looks simulated) | Critical | Data Analytics / Project Management / data owner | OPEN | Escalated: needs real outcome data; cannot be fixed by modelling
I7 | No Admissions table: admission is modelled through a proxy (Emergency & Severe) | Critical | Project Management / data owner | OPEN | Obtain Admissions, Referrals, Laboratory and Prescriptions tables
I8 | No attendance / no-show field in the supplied tables, so the Week 7 brief's attendance questions cannot be tested on this dataset | Critical | Project Management / Data Analytics | OPEN | Confirm which dataset the pod uses for attendance; harness is ready to re-run
I9 | Only 5,000 of 60,000 transactions link to an appointment; 22% of patients appear; Follow-Up visits without earlier visits (88%, confirmed by Data Analytics: the Follow-Up label does not reflect history) | High | Data Analytics / data owner | OPEN | Repair appointment keys; re-extract full history
I10 | Diagnosis is recorded at consultation, so a booking-time model cannot use it | Medium | Data Science / ML Engineering | OPEN | Decide prediction time-point before Week 8 integration
I11 | Week 5 baseline model not available in the supplied files | Low | Data Science | OPEN | Prevalence baseline and logistic regression used as reference points
I12 | Uneven flagging by age band (flag rate gap 36 pp, AC10 fails before and after) although accuracy is the same in every group | Medium | Data Science | OPEN | Moot while the model is not deployed; re-run parity checks once a real signal exists

## Decision log
ID | Decision | Reason
D1 | Acceptance criteria fixed before testing; test set locked and used once per model version | Prevents tuning to the test data
D2 | Model chosen on training data only; simplest model within 1 SE of the best (C. Ridge logistic, 10 reliable features) | Parsimony; no evidence of benefit from complexity
D3 | Remove FacilityID, DepartmentName, BMI_clean, DeptWorkloadIndex | Unreliable links (T11a); no AUC loss (T11b)
D4 | Operating point = flag-rate budget (top 20%), reported with lift | F1 threshold degenerates to flag-all when there is no signal
D5 | Do NOT release the model for any operational use; release only the tested interface and harness | Gate FAIL on mandatory criteria
D6 | Do not search for a more 'successful' target after the scan; the Week 6 proxy stays the reference | Avoid p-hacking: 9 targets scanned with Bonferroni intervals, none detected
D7 | Report the Data Analytics validation as a two-way cross-track test and the ML Engineering interface test as Data Science side only (no counterpart available) | Only activities that actually happened are claimed

## Week 8 actions
ID | Action before / during Week 8 | Owner | When
W8-1 | Obtain Admissions / Referrals / Attendance outcome data and re-run notebook sections 2-5 unchanged | Project Management / data owner | Before final integration
W8-2 | ML Engineering (when assigned) runs hc_contract_tests.py inside the pipeline and returns the result; fix any mismatch | ML Engineering / Project Management | Early Week 8
W8-3 | Agree the prediction time-point (booking vs after consultation) and the allowed feature list | Data Science + ML Engineering (once a counterpart is assigned) | Early Week 8
W8-4 | Data Analytics confirms the follow-up/prior-visit finding and repairs appointment keys | Data Analytics | Week 8
W8-5 | Present the HealthConnect model as 'validated null result + reusable test harness', not as a prediction tool | All tracks | Final presentation
W8-6 | Add fairness checks by sex, age band and province once a signal exists | Data Science | After real data

## Target scan
Target | n | Prevalence | AUC | CI_lo | CI_hi | Signal
Admission proxy (Emergency & Severe) [Week 6 target] | 5000 | 0.1088 | 0.4931 | 0.4702 | 0.5369 | none
Emergency visit | 5000 | 0.33 | 0.4961 | 0.4735 | 0.52 | none
Severe diagnosis | 5000 | 0.3244 | 0.4897 | 0.4616 | 0.5124 | none
Follow-Up visit | 5000 | 0.3388 | 0.4907 | 0.4828 | 0.529 | none
Returning patient (PriorVisits>0) | 5000 | 0.1114 | 0.6758 | 0.642 | 0.7006 | DETECTED
Returning patient, month removed (artifact check) | 5000 | 0.1114 | 0.4982 | 0.4554 | 0.5256 | none
High bill (top tertile) | 5000 | 0.3302 | 0.4948 | 0.4786 | 0.5271 | none
Underpaid bill (outstanding > 0) | 5000 | 0.2004 | 0.4969 | 0.4684 | 0.5249 | none
Insurance claim still pending | 3521 | 0.4962 | 0.5072 | 0.4793 | 0.5288 | none
Low satisfaction (rating 1-2) | 1756 | 0.4095 | 0.4549 | 0.4101 | 0.4887 | none
POSITIVE CONTROL: Age >= 65 | 5000 | 0.2942 | 0.9998 | 0.9996 | 0.9999 | DETECTED
POSITIVE CONTROL: rule-based high-risk flag | 5000 | 0.4144 | 0.8593 | 0.8458 | 0.8709 | DETECTED

## Segments
Variable | Level | n | Positives | Prevalence | AUC | AUC_lo | AUC_hi | FlagRate | Recall | Precision | Lift
Gender | Female | 2459 | 268 | 0.109 | 0.5248 | 0.4872 | 0.5614 | 0.2025 | 0.2276 | 0.1225 | 1.1239
Gender | Male | 2541 | 276 | 0.1086 | 0.4851 | 0.4513 | 0.5216 | 0.1976 | 0.1957 | 0.1076 | 0.9903
AgeBand4 | 18-39 | 1168 | 149 | 0.1276 | 0.5033 | 0.4494 | 0.5498 | 0.3604 | 0.3557 | 0.1259 | 0.9868
AgeBand4 | 40-59 | 1122 | 121 | 0.1078 | 0.4927 | 0.4434 | 0.5416 | 0.1711 | 0.1653 | 0.1042 | 0.9659
AgeBand4 | 60+ | 1740 | 172 | 0.0989 | 0.5134 | 0.4699 | 0.5602 | 0.1356 | 0.1512 | 0.1102 | 1.1145
AgeBand4 | <18 | 970 | 102 | 0.1052 | 0.4526 | 0.3871 | 0.5105 | 0.1557 | 0.1569 | 0.106 | 1.0077
ProvinceName | Eastern | 1006 | 120 | 0.1193 | 0.4956 | 0.4485 | 0.5513 | 0.2346 | 0.25 | 0.1271 | 1.0657
ProvinceName | Kigali City | 944 | 106 | 0.1123 | 0.4984 | 0.4406 | 0.5576 | 0.215 | 0.2075 | 0.1084 | 0.9651
ProvinceName | Northern | 1021 | 108 | 0.1058 | 0.4984 | 0.4406 | 0.5612 | 0.1959 | 0.2037 | 0.11 | 1.0399
ProvinceName | Southern | 978 | 95 | 0.0971 | 0.5099 | 0.45 | 0.5901 | 0.1524 | 0.1579 | 0.1007 | 1.0364
ProvinceName | Western | 1051 | 115 | 0.1094 | 0.506 | 0.4459 | 0.5654 | 0.2017 | 0.2261 | 0.1226 | 1.1208
ChronicCondition | Asthma | 1259 | 124 | 0.0985 | 0.5284 | 0.4716 | 0.5786 | 0.1763 | 0.2177 | 0.1216 | 1.2349
ChronicCondition | Diabetes | 1216 | 132 | 0.1086 | 0.4975 | 0.4453 | 0.5437 | 0.2031 | 0.1742 | 0.0931 | 0.8578
ChronicCondition | Hypertension | 1262 | 149 | 0.1181 | 0.5063 | 0.4582 | 0.5552 | 0.2282 | 0.2617 | 0.1354 | 1.147
ChronicCondition | None | 1263 | 139 | 0.1101 | 0.4838 | 0.4239 | 0.5283 | 0.1924 | 0.1871 | 0.107 | 0.9722
Diagnosis | Diabetes | 985 | 110 | 0.1117 | 0.4963 | 0.4389 | 0.5504 | 0.2152 | 0.2455 | 0.1274 | 1.1404
Diagnosis | Gastritis | 1017 | 98 | 0.0964 | 0.515 | 0.4588 | 0.5802 | 0.1495 | 0.1939 | 0.125 | 1.2972
Diagnosis | Hypertension | 1059 | 111 | 0.1048 | 0.5035 | 0.4543 | 0.5647 | 0.1955 | 0.1712 | 0.0918 | 0.8757
Diagnosis | Malaria | 935 | 109 | 0.1166 | 0.5213 | 0.463 | 0.5853 | 0.2086 | 0.2569 | 0.1436 | 1.2317
Diagnosis | Upper Respiratory Infection | 1004 | 116 | 0.1155 | 0.4768 | 0.4152 | 0.5247 | 0.2331 | 0.1897 | 0.094 | 0.8137
DepartmentName | Cardiology | 544 | 65 | 0.1195 | 0.5849 | 0.5195 | 0.6438 | 0.1967 | 0.2462 | 0.1495 | 1.2515
DepartmentName | Emergency | 495 | 54 | 0.1091 | 0.5061 | 0.4259 | 0.596 | 0.1939 | 0.1667 | 0.0938 | 0.8594
DepartmentName | ICU | 467 | 48 | 0.1028 | 0.4228 | 0.3338 | 0.5063 | 0.1713 | 0.1458 | 0.0875 | 0.8513
DepartmentName | Internal Medicine | 490 | 54 | 0.1102 | 0.5229 | 0.4428 | 0.6016 | 0.198 | 0.2037 | 0.1134 | 1.029
DepartmentName | Laboratory | 499 | 55 | 0.1102 | 0.5857 | 0.5098 | 0.6533 | 0.1884 | 0.2545 | 0.1489 | 1.3513
DepartmentName | Obstetrics & Gynecology | 511 | 66 | 0.1292 | 0.529 | 0.4532 | 0.6076 | 0.2857 | 0.3485 | 0.1575 | 1.2197
DepartmentName | Pediatrics | 491 | 56 | 0.1141 | 0.4409 | 0.3591 | 0.5236 | 0.1996 | 0.1607 | 0.0918 | 0.8052
DepartmentName | Pharmacy | 490 | 51 | 0.1041 | 0.5295 | 0.4335 | 0.6132 | 0.2245 | 0.2745 | 0.1273 | 1.2228
DepartmentName | Radiology | 525 | 46 | 0.0876 | 0.3636 | 0.2767 | 0.4569 | 0.1467 | 0.087 | 0.0519 | 0.5929
DepartmentName | Surgery | 488 | 49 | 0.1004 | 0.4889 | 0.4081 | 0.5665 | 0.1947 | 0.1633 | 0.0842 | 0.8387
FacilityID | HF001 | 273 | 32 | 0.1172 | 0.3788 | 0.2646 | 0.4802 | 0.1941 | 0.0938 | 0.0566 | 0.4829
FacilityID | HF002 | 241 | 25 | 0.1037 | 0.4187 | 0.3039 | 0.5226 | 0.195 | 0.12 | 0.0638 | 0.6153
FacilityID | HF003 | 256 | 27 | 0.1055 | 0.4993 | 0.3718 | 0.5972 | 0.207 | 0.1852 | 0.0943 | 0.8945
FacilityID | HF004 | 222 | 34 | 0.1532 | 0.5937 | 0.4884 | 0.6896 | 0.3829 | 0.5 | 0.2 | 1.3059
FacilityID | HF005 | 223 | 19 | 0.0852 | 0.4696 | 0.3403 | 0.5986 | 0.1525 | 0.1579 | 0.0882 | 1.0356
FacilityID | HF006 | 269 | 32 | 0.119 | 0.4643 | 0.3519 | 0.5556 | 0.1822 | 0.0938 | 0.0612 | 0.5147
FacilityID | HF007 | 224 | 24 | 0.1071 | 0.5504 | 0.4252 | 0.6658 | 0.1607 | 0.125 | 0.0833 | 0.7778
FacilityID | HF008 | 257 | 18 | 0.07 | 0.5119 | 0.385 | 0.6397 | 0.07 | 0.0556 | 0.0556 | 0.7932
FacilityID | HF009 | 241 | 27 | 0.112 | 0.4829 | 0.3522 | 0.6332 | 0.1784 | 0.3333 | 0.2093 | 1.8682
FacilityID | HF010 | 275 | 34 | 0.1236 | 0.4985 | 0.4005 | 0.6143 | 0.2727 | 0.3235 | 0.1467 | 1.1863
FacilityID | HF011 | 273 | 23 | 0.0842 | 0.419 | 0.2972 | 0.5458 | 0.1538 | 0 | 0 | 0
FacilityID | HF012 | 249 | 30 | 0.1205 | 0.419 | 0.313 | 0.5428 | 0.1847 | 0.1667 | 0.1087 | 0.9022
FacilityID | HF013 | 278 | 33 | 0.1187 | 0.4271 | 0.3188 | 0.5345 | 0.2122 | 0.1818 | 0.1017 | 0.8567
FacilityID | HF014 | 276 | 34 | 0.1232 | 0.4099 | 0.3061 | 0.5203 | 0.2138 | 0.1765 | 0.1017 | 0.8255
FacilityID | HF015 | 245 | 19 | 0.0776 | 0.4895 | 0.3404 | 0.6332 | 0.1061 | 0.1053 | 0.0769 | 0.9919
FacilityID | HF016 | 261 | 40 | 0.1533 | 0.5126 | 0.4133 | 0.6013 | 0.5249 | 0.55 | 0.1606 | 1.0478
FacilityID | HF017 | 243 | 29 | 0.1193 | 0.5943 | 0.4997 | 0.6962 | 0.1728 | 0.2414 | 0.1667 | 1.3966
FacilityID | HF018 | 240 | 24 | 0.1 | 0.6003 | 0.4888 | 0.7022 | 0.1583 | 0.2083 | 0.1316 | 1.3158
FacilityID | HF019 | 217 | 18 | 0.0829 | 0.5706 | 0.4592 | 0.6786 | 0.1244 | 0.1667 | 0.1111 | 1.3395
FacilityID | HF020 | 237 | 22 | 0.0928 | 0.4879 | 0.3669 | 0.6158 | 0.1308 | 0.0455 | 0.0323 | 0.3475

## Analytics cross-check
# | Data Analytics finding (Olabisi Amusan) | My Week 7 result | Agreement | Effect on the model / project
1 | 5,000 appointments vs 60,000 bills, diagnoses and payments; only 5,000 link via AppointmentID; linked records resemble unlinked ones | 55,000 orphan bills and diagnoses recomputed from raw files | AGREE | Appointment-level modelling stays at 5,000 rows. Their 'linked resembles unlinked' point is new: it supports treating the 5,000 as a fair sample (taken as reported, not retested by me)
2 | FacilityID differs from the department's facility in 4,744 of 5,000 appointments; same conflict in staff records (1,187 of 1,250) | 4,744 (94.9%) recomputed. I removed FacilityID and DepartmentName instead of substituting the department's facility | AGREE on count; different handling | Staff-record conflict is new: DoctorYears (doctor link) stays graded 'questionable'. Both approaches avoid the conflicting field
3 | No attended / missed / cancelled field, so a no-show target cannot be built | Same conclusion (issue I8) | AGREE | Confirmed by two tracks; escalated to Project Management
4 | Weak signal: severity independent of diagnosis (p=0.19), department (0.20), visit type (0.91); satisfaction by facility p=0.55, department 0.88, visit type 0.68; age vs visits 0.012 | Diagnosis vs severity p=0.214; satisfaction by facility p=0.795, by department 0.878; age vs billing/admission proxy rho near 0 | AGREE on conclusion; some p-values differ | Same finding: nothing is significant. P-values differ for facility satisfaction (0.55 vs 0.80) and diagnosis-severity (0.19 vs 0.21), probably from different tests or samples; not reconciled, conclusion unaffected
5 | Classes close to balanced (visit types about a third each; claims 50/50), so accuracy is weak | Week 6 EDA: same splits | AGREE | Already handled: model judged on AUC, PR-AUC, lift and permutation test, not accuracy
6 | Repeat visits rare: 4,443 patients, 5,000 appointments (average 1.13) | 22.2% of patients appear; PriorVisits mean 0.12 | AGREE | PriorVisits carries little information, consistent with its near-zero importance
7 | Phone numbers corrupted to scientific notation; every patient has an insurance ID | Same Week 6 data-quality findings | AGREE | Neither field used in the model
8 | Follow-up check: 88.0% of Follow-Up visits have no earlier visit (88.1% with strictly earlier dates); same for other visit types (89.3%); only 510 patients have more than one appointment | Recomputed 88.0% (Follow-Up) and 89.3% (others) | AGREE | Follow-Up label does not reflect visit history; VisitType already excluded from the model; PriorVisits stays a weak feature
9 | DoctorYears: doctor join is clean (100% of DoctorIDs found, 1-25 years) but doctor department matches the appointment department in only 0.6% and facility in 5.1%, about random | Week 6 data-quality finding: 5.14% facility match, 4,968 of 5,000 department mismatches | AGREE | DoctorYears kept as a doctor-level attribute only, never read as department or facility staffing
10 | Target: one diagnosis per appointment (join is safe); 544 of 5,000 positives (10.88%); 10.71% expected if Emergency and Severe were independent | Recomputed: observed 10.88% vs expected 10.71% | AGREE | New insight: the proxy behaves like two unrelated labels combined, which explains the chance-level AUC
11 | HasChronic check: 5,071 zeros and 14,929 ones ('None' is read as missing by default in pandas) | Verified: pipeline reads with keep_default_na=False; 1,263 'None' kept, 0 missing | AGREE | No change needed